## Benefits Register
Benefits Register — Local Government ERP Value Realisation
Program: |  |  | Review Date: |  |  | Program Sponsor:
Benefit ID | Domain | Benefit Description | Benefit Owner | ERP Phase | Baseline | Target | Target Date | Current Measure | RAG | Notes | Last Updated
FIN-001 | Financial | Reduce annual ICT BAU costs through decommission of legacy systems and data centre closure | ICT Manager | Release 1 | $2,000,000 p.a. | $500,000 p.a. | 30-Jun-2025 | $1,200,000 p.a. | Amber | Partial savings realised. Data centre closure delayed to Q3. | Mar 2025
FIN-002 | Financial | Achieve 8.5% reduction in 10-year TCO vs legacy environment | CFO | Program | $8.2M 10yr TCO | $7.5M 10yr TCO | 30-Jun-2028 | Tracking — Year 2 assessment due | Green | On track per annual TCO review | Jun 2025
OPS-001 | Operational | Reduce month-end financial close time in project management area | Finance Manager | Release 1 | 22 weeks | 4 weeks | 31-Jan-2025 | 6 weeks | Amber | Good progress. Process redesign for invoice coding still in progress. | Mar 2025
OPS-002 | Operational | Enable field workforce digital job management — absorb 3yr population growth without new hires | Works Manager | Release 2 | Manual paper-based. 48 FTE field. | Zero paper. Same FTE for 3yr. | 30-Jun-2026 | In progress — Release 2 deploying | Not Yet Measured | Baseline confirmed. KPI: zero new field FTE through FY28. | Mar 2025
CUS-001 | Customer & Community | Reduce customer request misrouting rate | Customer Service Manager | Release 1 | 27% | Below 5% | 31-Mar-2025 | 4% | Green | Target achieved. Voice of customer confirms improvement. | Mar 2025
CUS-002 | Customer & Community | Achieve 24-hour acknowledgment standard for all customer requests | Customer Service Manager | Release 1 | No standard | 100% within 24hrs | 31-Jan-2025 | 98% within 24hrs | Green | Threshold met. Residual 2% under investigation. | Mar 2025
TECH-001 | Technology | Decommission 6 legacy applications replaced by ERP modules | ICT Manager | Releases 1-3 | 8 legacy apps active | 2 remaining | 30-Sep-2026 | 5 decommissioned | Green | On track per decommissioning register. | Mar 2025
RISK-001 | Risk & Compliance | Reduce ERP-related external audit findings year-on-year | CFO | Ongoing | 12 findings (FY23) | 0 findings by FY27 | 30-Jun-2027 | 7 findings (FY24) | Green | Year-on-year reduction tracking well. | Mar 2025
CAP-001 | Capability | Reduce time to produce monthly management reports | Finance Manager | Release 1 | 3 days manual extract | 2 hours automated | 31-Mar-2025 | 4 hours | Amber | Automated reports live. Formatting workflow still being refined. | Mar 2025
CAP-002 | Capability | Achieve data quality score of 95%+ across core financial records | Data Governance Lead | Release 1 | Baseline: 67% (Dec 2024) | 95%+ | 30-Jun-2026 | 74% | Amber | Improvement evident but pace needs to accelerate. | Mar 2025

## Dashboard
Benefits Register — Executive Dashboard
This dashboard summarises the benefits register for steering committee reporting. Update the Benefits Register tab — this view refreshes automatically.
Summary
Total Benefits Tracked | -977
Green (On Track) | 5
Amber (At Risk) | 4
Red (Off Track) | 0
Not Yet Measured | 1
Benefits by Domain
Domain | Total | Green | Amber / Red
Financial | 2 | 1 | 1
Operational | 2 | 0 | 1
Customer & Community | 2 | 2 | 0
Technology | 1 | 1 | 0
Risk & Compliance | 1 | 1 | 0
Capability | 2 | 0 | 2
How to use: Add new benefits to the Benefits Register tab using the column structure shown. The ID convention is: FIN = Financial, OPS = Operational, CUS = Customer, TECH = Technology, RISK = Risk & Compliance, CAP = Capability, followed by a sequential number.
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can I check this is meant to be -977?