## RACI Matrix
Benefits & Value Realisation RACI — Local Government ERP Program
R = Responsible (does the work) A = Accountable (owns the outcome) C = Consulted I = Informed — = Not involved
Activity / Phase | CEO / GM | CFO | CIO / IT Lead | PMO Lead | Business Unit Managers | Change Manager | IT Operations | Implementation Partner | Independent QA
STRATEGY & BUSINESS CASE
Develop and own ERP strategy | A | I | R | C | C | — | — | — | —
Author initial business case | A | C | C | R | C | — | — | — | —
Approve business case for funding | A | A | C | I | I | — | — | — | —
Select ERP platform | A | C | C | R | C | — | — | C | —
Select implementation partner | A | C | C | R | — | — | — | — | —
Scope and approve independent QA | A | C | C | R | — | — | — | — | C
PROGRAM INITIATION
Establish program governance | A | C | C | R | I | I | — | C | —
Designate formal benefit owners | A | A | C | R | A | C | — | — | —
Create initial benefits register | I | C | C | R | C | R | — | — | —
Establish baseline value metrics | I | C | C | R | R | R | C | — | C
Onboard executive stakeholders | A | A | A | R | I | C | — | — | —
PER-PHASE BENEFITS IDENTIFICATION
Prepare process playbook for phase | — | — | I | R | — | R | C | C | —
Facilitate whiteboard sessions | — | — | I | C | R | R | — | C | —
Document value targets per phase | — | C | I | R | C | R | — | — | —
Update benefits and value targets register | I | C | C | R | C | R | — | — | —
Confirm benefit & value realisation owner accountability | A | A | C | R | A | C | — | — | —
Design change program per benefit with value target | — | — | I | C | C | R | — | — | —
ERP DEPLOYMENT
Configure and deploy ERP modules | — | — | A | C | — | — | R | R | I
Execute change and training program | I | I | I | C | R | R | C | C | —
Conduct independent QA review | I | I | I | A | — | — | — | — | R
Report QA findings to board | A | I | C | R | — | — | — | — | R
Go-live authorisation | A | A | A | R | C | C | I | C | C
MEASUREMENT & REPORTING
Collect value measurements | — | — | — | C | R | R | C | — | —
Update RAG status in register | — | C | C | R | R | R | — | — | —
Quarterly PDCA check-in facilitation | — | C | C | R | C | R | — | — | —
Steering committee value realisation report | A | I | I | R | I | C | — | — | —
Annual benefits realisation review | A | A | A | R | C | C | — | — | C
BAU TRANSITION
Redesign IT operating model | A | C | A | C | — | — | R | C | —
Transfer register to BI function | A | C | C | R | — | R | — | — | —
Ongoing CDT cadence (post-project) | I | C | C | — | A | R | C | — | —
New executive onboarding process | A | A | A | R | — | C | — | — | —
Annual maturity self-assessment | I | C | C | A | C | R | — | — | —

## Legend & Guide
RACI Legend and Guidance
Code | Meaning | Guidance
R | Responsible | The person or role who does the work. There can be multiple R for a single activity.
A | Accountable | The person who owns the outcome and is answerable for the result. There must be exactly ONE A per activity.
C | Consulted | People who should provide input before the work is done. Two-way communication required.
I | Informed | People who should be kept informed after the work is done. One-way communication only.
— | Not involved | This role has no involvement in this activity.